	[image: image1.png]Australian Government

Australian Institute of Criminology





[image: image1.png]




PROJECT COMPLETION FORM
	Project number  118
	Project title The deterrent value of firearms

	Timeline

Start date: 17 October 2005
End date: 8 March 2006
	Project completed on time
No
Reasons for delays? Project delayed by 3 weeks (waiting on feedback from Chubb and report amendments required)


	Funding 
Amount: $10,000 (excluding GST)
Source: Chubb
	Final payment received
Yes
Any problems?



	Key products
In-confidence consultancy report
	Final product done
Yes
Any problems?

Anything outstanding?




Records
	Dataset number(s) (if applicable)
	N/A

	Lodgement in the library 
	Dataset 
N/A
Codebook
N/A
Questionnaire
N/A
Syntax
N/A
Retention details/owner



	Details of outputs provided to library 

	Publications
N/A
Presentations
N/A
Consultancy reports
N/A
Roundtable reports
N/A

	Please specify any restricted access to datasets or products and reasons
	Consultancy report is in-confidence only

	Project files and records been tidied up on DME 
	Yes
	Date to be archived:
On completion of project/
Period after completion: TBA
	Date to be destroyed:
Period after completion: TBA

	Client Satisfaction Survey given to client
	
Yes

	Examples of impact/outcomes provided to Research manager
	
Yes (via email)

	Signatures and dates
1. Project officer
2. Research manager
3. Information services manager
	..............................................................................
..............................................................................

..............................................................................


::ODMA\DME-MSE\AIC-23367
1
PAGE  
2
::ODMA\DME-MSE\AIC-13033

